## PFS Work Plan
Logo Here |  |  |  | Work
Project Workplan: | Name of Project Here |  |  | Status as of | 2019-02-06 |  | Legend
|  |  |  | *Starts Jan 1, 2018 |  |  | Decision Point |  | n
[7 empty] | Deliverable |  | u
Activity Header
[33 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Activity/Task |  | Key Decision Point ? | Final Deliverable ? | Start Date | Finish Date | Planned Duration (Days) | Status | Completion Date | Task Owner | Associated Deliverable(s) | time axis 2018-01-01 to 2019-01-02
[11 empty] | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03
1.0 | Outcomes & Financial Model |  |  | 2018-01-01 | 2018-08-20 | 166
1.1 | Outcomes and Budget Model |  |  | 2018-01-01 | 2018-07-31 | 152
1.11 | Finalize first draft of outcomes & budget model including outcomes values, timing and frequency and youth eligibility |  |  | 2018-01-23 | 2018-06-01 | 94 |  |  | Transaction Structurer | Budget Model & Outcomes Slides
1.12 | Budget and Outcomes Review by Working Group and Evaluator to review calculation of outcomes payments and maximum payment amounts per outcome, as applicable. Comments to be returned to Transaction Structurer by the Finish Date | Y |  | 2018-02-07 | 2018-06-13 | 91 |  |  | Working Group, Evaluator | Consolidated comments on outcomes & project budget | bar: 2018-06-13
1.13 | Revisions by Transaction Structurer and second draft circulated |  |  | 2018-02-15 | 2018-07-02 | 100 |  |  | Transaction Structurer
1.14 | Budget and Outcomes Review by Working Group |  |  | 2018-06-13 | 2018-07-18 | 26 |  |  | Working Group, Evaluator
1.15 | Budget and Outcomes circulated to Executive Committee |  |  | 2018-07-18 | 2018-07-23 | 6 |  |  | Executive Committee
1.16 | Final comments due to Transaction Structurer from Working Group and Executive Committee | Y |  | 2018-07-18 | 2018-07-23 | 6 |  |  | Working Group, Executive Committee | bar: 2018-07-23
1.17 | Final internal sign-off period on outcomes & budget (no substantive changes to be made) |  | Y | 2018-07-23 | 2018-07-31 | 7 |  |  | Transaction Structurer | Outcomes & Budget | bar: 2018-07-31
1.2 | Financial Modeling |  |  | 2018-02-28 | 2018-08-15 | 121
1.21 | First draft of capital stack, including senior, junior, recoverable grant or grant funding needs and pay-in schedule of government outcomes, in tandem with final review of budget and outcomes |  |  | 2018-02-28 | 2018-07-10 | 97 |  |  | Transaction Structurer
1.22 | First draft of financial model reviewed by Working Group | Y |  | 2018-03-14 | 2018-07-10 | 87 |  |  | Working Group | bar: 2018-07-10
1.23 | Revision by Transaction Structurer |  |  | 2018-07-10 | 2018-07-23 | 12 |  |  | Transaction Structurer
1.24 | Second draft Financial Model reviewed by Working Group |  |  | 2018-07-31 | 2018-08-10 | 9 |  |  | Working Group
1.25 | Financial Model circulated to Executive Committee | Y |  | 2018-08-23 | 2018-08-23 | 1 |  |  | Executive Committee | bar: 2018-08-23
1.26 | Final comments due to Transaction Structurer from Working Group and Executive Committee |  |  | 2018-08-23 | 2018-08-30 | 6 |  |  | Transaction Structurer
1.27 | Final internal sign-off period on pay-in schedule of government outcomes |  | Y | 2018-08-30 | 2018-09-05 | 7 |  |  | Executive Committee | Financial Model | bar: 2018-09-05
2.0 | Back-end Payor |  |  | 2018-01-23 | 2018-10-01 | 182
2.1 | Pay for Success Governance Committee |  |  | 2018-01-23 | 2018-02-07 | 12
2.11 | Finalize proposed Executive Committee & Working Groups | Y |  | 2018-01-23 | 2018-02-05 | 12 |  |  | Government Champion | bar: 2018-02-05
2.2 | Payment Mechanism |  |  | 2018-01-23 | 2018-09-05 | 162
2.21 | Review internal process for payment mechanism |  |  | 2018-02-05 | 2018-09-05 | 153 |  |  | Government Champion
2.22 | Submit first year Appropriation Request to government based on first draft of outcomes |  |  | 2018-02-07 | 2018-09-10 | 156 |  |  | Transaction Structurer
2.23 | Finalize initial Appropriation Request | Y |  | 2018-01-23 | 2018-09-14 | 169 |  |  | Government Champion | bar: 2018-09-14
2.24 | Draft funding plan for government, including identifying set asides and policy / legislative concerns |  |  | 2018-02-28 | 2018-08-10 | 118 |  |  | Transaction Structurer, Service Provider Working Group
2.25 | Finalize funding plan between service provider, intermediary / transaction structurer and government | Y | Y | 2018-04-13 | 2018-09-05 | 106 |  |  | Government Champion | Funding Plan | bar: 2018-09-05
3.0 | Evaluation |  |  | 2018-01-23 | 2018-09-04 | 161
3.1 | Evaluation Plan |  |  | 2018-01-23 | 2018-05-25 | 89
3.11 | Determine evaluation methodology, and roles of parties | Y |  | 2018-01-23 | 2018-07-10 | 121 |  |  | Evaluator, Service Provider, Transaction Structurer | bar: 2018-07-10
3.12 | First draft evaluation plan, including: Intake, referral and randomization procedures Tie into of outcome measurements for payments Third Party Validation of process, if necessary |  |  | 2018-02-28 | 2018-08-01 | 111 |  |  | Evaluator
3.13 | First draft circulated for review by Working Group, Transaction Structurer and Service Provider |  |  | 2018-08-01 | 2018-08-15 | 11 |  |  | Working Group, Transaction Structurer, Service Provider
3.14 | Revisions by Evaluator |  |  | 2018-08-15 | 2018-09-05 | 16 |  |  | Evaluator
3.15 | Second draft circulated to be reviewed by Working Group, Service Provider and Transaction Structurer |  |  | 2018-09-05 | 2018-09-19 | 11 |  |  | Working Group, Transaction Structurer, Service Provider
3.16 | Review by Executive Committee | Y |  | 2018-09-19 | 2018-09-28 | 8 |  |  | Executive Committee | bar: 2018-09-28
3.17 | Final Comments due to Evaluator by all parties |  |  | 2018-09-28 | 2018-10-08 | 9 |  |  | Evaluator
3.18 | Final internal sign-off |  | Y | 2018-10-08 | 2018-10-08 | 1 |  |  | Executive Committee | Evaluation Plan | bar: 2018-10-08
3.2 | Access to administrative data and Data Sharing agreements |  |  | 2018-01-23 | 2018-08-06 | 142
3.21 | Review internal IT databases for PFS data capture (Service Provider and Government Entities) |  |  | 2018-01-23 | 2018-08-15 | 147 |  |  | Evaluator | Data system support (RFP and SOW, tbd)
3.22 | Coordinate data sharing agreements and infrastructure for evaluation, including any polices related to data security and transmission of data |  |  | 2018-01-23 | 2018-08-20 | 152 |  |  | Evaluator
3.23 | Execute data sharing agreements |  | Y | 2018-10-15 | 2018-11-30 | 35 |  |  | Working Group, Executive Committee, Transaction Structurer, Legal, Service Provider | Data sharing agreement(s) | bar: 2018-11-30
3.4 | RFP for External Validator / Evaluator (as needed) |  |  | 2018-08-15 | 2018-09-14 | 23 |  |  |  | TBD
4.0 | Service Provider |  |  | 2018-01-23 | 2019-01-02 | 247
4.1 | Program Implementation Plan / Operations Plan |  |  | 2018-01-23 | 2018-07-31 | 136
4.11 | First draft of program implementation plan circulated for review, includes: Specifying workspace, equipment, employee & consultant resources Defining services and community partners Defining screening, eligibility and treatment of participants |  |  | 2018-01-23 | 2018-02-06 | 11 |  |  | Transaction Structurer, Service Provider
4.12 | Document review by Working Group | Y |  | 2018-02-06 | 2018-02-28 | 17 |  |  | Working Group | bar: 2018-02-28
4.13 | Revision by Transaction Structurer & Service Provider |  |  | 2018-02-28 | 2018-04-02 | 26 |  |  | Service Provider, Transaction Structurer
4.14 | Final draft comment period, all parties (will tie into evaluation) | Y | Y | 2018-04-02 | 2018-07-31 | 87 |  |  | Working Group, Executive Committee | Program Implementation Plan | bar: 2018-07-31
4.2 | Project Ramp-up |  |  | 2018-10-01 | 2019-01-02 | 68
4.21 | Hire and train new staff identified in implementation plan |  | Y | 2018-10-01 | 2019-01-02 | 68 |  |  | Service Provider | Job descriptions | bar: 2019-01-02
4.22 | Formalize relationships with community partners through MOUs, as necessary |  | Y | 2018-08-15 | 2018-10-01 | 36 |  |  | Service Provider, Working Group | MOU with community partners | bar: 2018-10-01
4.23 | Build pipeline of eligible participants |  |  | 2018-08-15 | 2018-11-01 | 57 |  |  | Service Provider, Working Group (as necessary)
4.3 | Project Launch |  |  | 2019-01-02 | 2019-01-02 | 1
5.0 | Legal Contracting |  |  | 2018-02-07 | 2019-01-02 | 236
5.1 | Finalize roles, responsibilities and deliverables through program term sheet, to tie into legal contracting |  |  | 2018-02-07 | 2018-09-05 | 151 |  |  | Service Provider, Working Group, Transaction Structurer, Legal | Project Term Sheet
5.2 | Special Purpose Vehicle determination and formation (intermediary structure) with final sign-off from Executive Committee | Y |  | 2018-03-01 | 2018-07-23 | 105 |  |  | Transaction Structurer, Executive Committee, Legal | bar: 2018-07-23
5.3 | PFS Contract & Service Provider Agreement |  |  | 2018-05-28 | 2019-01-02 | 158 |  |  |  | PFS Contract & Service Provider Agreement
5.31 | Define key PFS contract terms including schedules for (to be driven from above deliverables) Program Operations Governance (post-launch) Program Evaluation Calculation of Outcomes Payments | Y |  | 2018-07-31 | 2018-10-10 | 52 |  |  | Transaction Structurer, Service Provider, Working Group, Legal | Appendices including: Program Operations, Governance Structurer, Evaluation Summary & Outcomes Summary | bar: 2018-10-10
5.32 | First draft of PFS Contract & Service Provider agreement |  |  | 2018-09-05 | 2018-09-05 | 1
5.33 | Document review by Service Provider and Government and comments returned to Legal by Finish Date | Y |  | 2018-09-05 | 2018-09-24 | 16 |  |  | Service Provider, Working Group | bar: 2018-09-24
5.34 | Revisions by Legal |  |  | 2018-09-24 | 2018-10-05 | 10 |  |  | Transaction Structurer, Legal
5.35 | First draft of PFS Contract & Service Provider agreement circulated to Funders |  |  | 2018-10-05 | 2018-10-05 | 1
5.36 | Document review by Funders and comments due back to Legal, substantive changes to be reviewed with Service Provider and Government |  |  | 2018-10-05 | 2018-10-15 | 9 |  |  | Funders
5.37 | Final Revisions by Legal with final draft of PFS Contract and Service Provider Agreement circulated to all project parties |  | Y | 2018-10-15 | 2018-11-01 | 14 |  |  | Transaction Structurer, Legal | bar: 2018-11-01
5.38 | Final internal sign-off period | Y |  | 2018-11-01 | 2018-12-01 | 23 |  |  | Executive Committee | bar: 2018-12-01
5.4 | Validator / Evaluator Agreement |  |  | 2018-09-05 | 2018-12-01 | 64
5.41 | First draft of Validator / Evaluator Agreement |  |  | 2018-09-05 | 2018-10-15 | 31 |  |  | TBD Evaluator / Validator, Transaction Structurer, Legal
5.42 | Validator / Evaluator agreement circulated to Service Provider & Working Group with comments due to Legal by Finish Date |  |  | 2018-10-15 | 2018-11-01 | 14 |  |  | Service Provider, Working Group
5.43 | Validator / Evaluator agreement circulated to Funders with comments due to Legal by Finish Date |  |  | 2018-11-15 | 2018-12-01 | 13 |  |  | Funders
5.44 | Final internal sign-off period | Y |  | 2018-12-01 | 2018-12-15 | 11 |  |  | Executive Committee | bar: 2018-12-15
5.5 | PFS Contract executed |  | Y | 2019-01-02 | 2019-01-02 | 1 |  |  | Executive Committee, Transaction Structurer / Intermediary, Service Provider | PFS Contract | bar: 2019-01-02
5.6 | Validator / Evaluator agreement signed |  | Y | 2019-01-02 | 2019-01-02 | 1 |  |  | Service Provider, Transaction Structurer, Evaluator | Validator / Evaluator Agreement | bar: 2019-01-02
5.7 | Service Provider Agreement executed |  | Y | 2019-01-02 | 2019-01-02 | 1 |  |  | Service Provider, Intermediary / Transaction Structurer | Service Provider Agreement | bar: 2019-01-02
5.8 | Investor documentation executed |  | Y | 2019-01-02 | 2019-01-02 | 1 |  |  | Intermediary / Transaction Structurer, Funders | Investor Documentation (see under investor) | bar: 2019-01-02
5.9 | Publicity agreement |  | Y | 2019-01-02 | 2019-01-02 | 1 |  |  | Executive Committee, Transaction Structurer / Intermediary, Service Provider | Publicity agreement | bar: 2019-01-02
5.101 | Escrow agreement |  | Y | 2019-01-02 | 2019-01-02 | 1 |  |  | Executive Committee, Transaction Structurer / Intermediary, Service Provider | Escrow agreement | bar: 2019-01-02
6.0 | Investor Outreach and Contracting |  |  | 2018-01-23 | 2019-01-02 | 247
6.1 | Investor outreach and research, including understanding investor interest areas and funding constraints (dollar thresholds, approval and closing timelines / costs, interest rates, any constraints) |  |  | 2018-01-23 | 2018-09-05 | 162 |  |  | Transaction Structurer
6.2 | Develop first draft of investor term sheet and due diligence materials that includes outcomes, pricing, capital structure, success payment triggers and payment schedules |  |  | 2018-02-05 | 2018-08-20 | 141 |  |  | Transaction Structurer | Due Diligence Package
6.3 | Initiate Funder Due Diligence and Underwriting |  |  | 2018-04-02 | 2018-09-20 | 124
6.31 | Hold first investor convening and site visit to review program model and initial project terms |  |  | 2018-08-30 | 2018-09-30 | 24 |  |  | Funders, Executive Committee, Service Provider, Transaction Structurer | Funder Convening Presentation & Agenda
6.32 | Create final due diligence package for investors, including financial model |  |  | 2018-04-02 | 2018-09-05 | 113 |  |  | Transaction Structurer | Due Diligence Package, Financing Term Sheet, Financial Model, NDA
6.33 | Due Diligence Q&A Period |  |  | 2018-09-05 | 2018-10-08 | 26 |  |  | Transaction Structurer w/ Service Provider input
6.34 | Initial Funding Commitments |  |  | 2018-10-08 | 2018-10-08 | 1 |  |  | Funders | Letter of Intent
6.35 | Formal Funding Commitments |  |  | 2018-10-31 | 2018-10-31 | 1 |  |  | Funders | Commitment Letter
6.4 | Investor Documentation |  |  | 2018-10-31 | 2018-12-15 | 34
6.41 | Investor documentation and negotiation |  | Y | 2018-10-31 | 2018-12-01 | 24 |  |  | Funders, Transaction Structurer, Legal | Loan and / or grant agreement | bar: 2018-12-01
6.42 | Loan and Grant Agreement executed |  | Y | 2018-12-14 | 2018-12-15 | 2 |  |  | Funders, Transaction Structurer, Legal | bar: 2018-12-15
6.43 | Intercreditor and subordination agreement executed |  | Y | 2018-12-15 | 2018-12-15 | 1 |  |  | Funders, Transaction Structurer, Legal | Intercreditor & subordination agreement | bar: 2018-12-15
6.44 | Pledge and security agreement executed |  | Y | 2018-12-15 | 2018-12-15 | 1 |  |  | Funders, Transaction Structurer, Legal | Pledge & security agreement | bar: 2018-12-15
7.0 | Program Management |  |  | 2018-01-23 | 2019-01-02 | 247
7.1 | Coordinate weekly calls with Transaction Structurer, Service Provider and Working Group |  |  | 2018-01-23 | 2018-02-02 | 9 |  |  | Transaction Structurer, Working Group, Executive Committee (as needed)
7.2 | Finalize Workplan |  |  | 2018-01-23 | 2018-02-07 | 12
7.21 | Draft Workplan with roles, responsibilities, deliverables and decision points |  |  | 2018-01-23 | 2018-01-31 | 7 |  |  | Transaction Structurer, Service Provider
7.22 | Review Workplan with roles, responsibilities, deliverables and decision points with comments due on Finish Date | Y |  | 2018-01-31 | 2018-06-20 | 101 |  |  | Transaction Structurer, Working Group, Service Provider, other parties as needed | bar: 2018-06-20
7.23 | Workplan finalized |  | Y | 2018-02-07 | 2018-06-25 | 101 |  |  | Transaction Structurer, Service Provider | Workplan | bar: 2018-06-25
7.3 | Weekly Program Management Status Calls |  |  |  |  | 1 |  |  | Transaction Structurer, Working Group, Service Provider, other parties as needed | Project Status Report
7.4 | PFS Overview Webinar (as needed) | [7 empty] | Transaction Structurer | TBD
7.5 | Executive Committee Updates
7.57 | Executive Committee Monthly Update |  |  | 2018-03-12 | 2018-03-16 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report
7.52 | Executive Committee Monthly Update |  |  | 2018-04-16 | 2018-04-16 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report
7.53 | Executive Committee Monthly Update |  |  | 2018-05-24 | 2018-05-24 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report
7.54 | Executive Committee Monthly Update |  |  | 2018-06-25 | 2018-06-25 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report
7.55 | Executive Committee Monthly Update |  |  | 2018-07-31 | 2018-07-31 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report
7.56 | Executive Committee Monthly Update |  |  | 2018-08-23 | 2018-08-23 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report
7.57 | Executive Committee Monthly Update |  |  | 2018-09-25 | 2018-09-25 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report
7.58 | Executive Committee Monthly Update |  |  | 2018-10-10 | 2018-10-14 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report
7.59 | Executive Committee Monthly Update |  |  | 2018-11-10 | 2018-11-14 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report
7.6 | Executive Committee Monthly Update |  |  | 2018-12-10 | 2018-12-14 |  |  |  | Executive Committee, Service Provider, Transaction Structurer | Status Report

## Deliverables List
Deliverable Log
# | Workstream | Deliverable Name | Deliverable Type | Description | Owner | Due Date | Requires Approval?
1 | Outcomes | Outcomes Scenarios
2 | Outcomes | Payment Mechanism / Legislative Authority
3 | Outcomes | MOU between back-end payor and service provider |  | Formal memorandum indicating the back-end payor(s)'s commitment and initial terms of agreement to fund outcomes payments
4 | Outcomes | Financial / Economic Model |  | Mathematical model representing and / or predicitng the performance of the Pay for Success program and its financial predicitons
5 | Evaluation | RFP to select evaluator | Word Document | RFP to identify and select a firm or organization that has experience evaluation evidenced-based social service programs to assist in evaluation design
6 | Evaluation | RFP to select validator | Word Document | RFP to identify and select a firm or organization that has experience validating evaluations of evidenced-based social service programs, if required
7 | Evaluation | RFP to select data consultant | Word Document
8 | Evaluation | Evaluation Plan | Word Document | Outline of evaluation criteria, performance measurement criteria and evaluation methodology
9 | Evaluation | Data Sharing Agreement | Word Document | Agreement between parties and evaluator defining parameters for sharing data needed under the Pay for Success agreement to evaluate success
10 | Evaluation | Data System | TBD
11 | Service Provider | RFP for Service Provider Capacity Building | Word Document | RFP to identify and select a firm / organization / individual with experience implementing programs at social service provider
12 | Service Provider | Operational Plan | Word Document | Includes Program Descripition and Workflow; Program Budget; Risk Assessment and Mitigation Strategy; Job Descriptions
13 | PFS Structure and Legal | Pay for Success Contract | Word Document | Contract between back-end payor and service provider and / or intermediary to create contracual structure outlining the terms of Pay for Success
14 | PFS Structure and Legal | Publicity Agreement | Word Document | Agreement guiding communications of public project details and specifics as part of the project launch, implementaiton and ongoing external presentation of the project
15 | PFS Structure and Legal | Escrow Agreement | Word Document | Agreement governing deposits of back-end payor payments and / or lender payments into an escrow account between contract parties and escrow agent
16 | PFS Structure and Legal | Service Provider Agreement | Word Document | Agreement between Service Provider and intermediary to govern the services and obligations of a service provider to provide services, as well as the required use of funds and reporting requirements
17 | PFS Structure and Legal | Loan Agreement and Corresponding Loan Documents | Word Document | Senior and junior loan documents
18 | PFS Structure and Legal | Grant Agreement | Word Document | Agreement governing grants used to fund and facilitate program services
19 | PFS Structure and Legal | Intercreditor and subordination Agreement | Word Document | Intercreditor and subordination agreement among the lenders and service provider / intermediary
20 | PFS Structure and Legal | Pledge and Security Agreement | Word Document | Pledge and security agreement between service provider / intermediary and lenders
21 | PFS Structure and Legal | Funding Plan | Word Document | Schedule of funding
22 | PFS Structure and Legal | Funding Disbursement Request Form | Excel Document | Funding disbursement request form for Service Provider to request funding from LLC
23 | PFS Structure and Legal | Financial Management and Oversight Agreement | Word Document | Agreement governing the distribution of funds received through grants, loans and success payments as well as general management and oversight of services
24 | PFS Structure and Legal | Reporting Templates | TBD
25 | PFS Structure and Legal | Governance Structure | TBD
26 | Investor | Term Sheet | Word Document | Document outline the terms by which an investor will make a financial investment in the Pay for Success Project
27 | Investor | Due Diligence Package and Financial Model | Word Document & Excel Model
28 | Investor | Funder Convenings / Site Visits | Event
29 | Investor | Letter of Intent | Word Document | Outlines terms of financing, serving as an agreement to agree between transaction parties
30 | Investor | Commitment Letter | Word Document | Letter indicating what terms of financing lenders will be offering project, indicating the loan has been approved.
31 | Investor | Executed grant / loan documents | Word Document
32 | Program Management | Bi-weekly Status Reports | PowerPoint
33 | Program Management | Service Provider Capacity Training | Event
34 | Program Management | Knowledge Sharing Deliverables, as necessary | Various