Assessing Community Development Program Performance:

Quantitative Assessment Strategies

for the LISC Sustainable Communities Initiative

Chris Walker

Francisca Winston

Sarah Rankin

Local Initiatives Support Corporation

Research and Assessment

November, 2009

TABLE OF CONTENTS

Assessing Community Development Program Performance:

Quantitative Assessment Strategies for the LISC Sustainable Communities Initiative

1.  Overview of the Sustainable Communities Initiative	3

2.  Research Questions and Approach	4

Analysis Questions	4

Characteristics of Neighborhoods	6

Development of Neighborhood Indicators	7

Indicators Used to Monitor Changes in Neighborhood Quality	8

Construction of Comparison Neighborhoods	9

Selection of Comparison Areas for National Monitoring	9

Selection of Comparison Areas for Local Assessment	11

Baselines to Compare Pre- and Post-Intervention Indicator Levels and Trends	13

3.  Summary of Data Sources, Uses, and Analysis Samples	14

National Neighborhood Monitoring Database	14

Local Neighborhood Indicator Systems	15

Analysis Samples	16

4.  Analysis and Reporting	16

Analysis Strategy	16

Reports	18

5.  Management and Workplan	19

Project Organization	19

Communication and Collaboration	20

National Partnerships	21

Work Tasks and Schedule	22

Assessing Community Development Program Performance:

Quantitative Assessment Strategies for the LISC Sustainable Communities Initiative

In July, 2007, LISC began its Sustainable Communities Initiative, an ambitious attempt to achieve the revitalization of whole neighborhoods in ways that convey enduring benefits to the low-income people who live in them.  This whole-community approach extends LISC’s previous work in community real estate and nonprofit capacity-building to a focus on the multiple and interconnected efforts needed effect more change more broadly.  The initiative draws heavily on the New Communities Program in Chicago, initiated in 2003.  As of November 2009, LISC had rolled out the initiative in 16 sites outside of Chicago: Bay Area, Detroit, Duluth, Kansas City, Indianapolis, Milwaukee, Rhode Island, Rural Pennsylvania, Twin Cities, Washington, DC, Newark, Houston, San Diego, New York City, and the Mid-South Delta.

This approach is not easy to implement, and it is not always clear when success has been achieved.   In the past, community development has suffered from its inability to develop clear and compelling statistical demonstrations of its value to neighborhoods.  But in the last ten years, researchers have begun to build the analytical and informational tools needed to do so; these now make it possible to examine neighborhood change on a scale not previously possible.

In early 2007, the LISC governing board directed the staff to assess the outcomes of the Sustainable Communities program.  This report describes how LISC researchers and consultants are determining whether neighborhoods have indeed changed in relation to what would otherwise be expected, and how those changes have been produced.   Learning how changes were produced is the subject of the qualitative portion of the analysis, described in more detail elsewhere.  But finding out whether changes were produced at all is the subject of the quantitative analysis, described in more detail in this document.  We describe where the quantitative assessment stands as of November, 2009.

The discussion proceeds through five sections:

Section 1:  Brief overview of the Sustainable Communities initiative and the multiple characteristics of communities that define the initiative’s outcomes for quantitative assessment purposes. Quantitative research covers 16 Sustainable Communities sites and neighborhoods as declared by November, 2009, including four impact sites, in which detailed neighborhood data produced by local data warehouses under contract to LISC are being analyzed.  (In Chicago, MDRC in New York in cooperation with the Chicago Metropolitan Communities Information Center is leading the quantitative research, under contract to the MacArthur Foundation.)

Section 2:  Discussion of research questions and approach, emphasizing the two basic tasks of monitoring neighborhood change indicators and assessing the effects Sustainable Communities programs may have had on those changes.   These two tasks require different, but complementary, approaches to indicator development, sources of data, definitions of analysis and comparison neighborhoods, and the numbers of sites involved.  (A summary of the differences between the two types of analysis is presented in Exhibit 1.)

- The monitoring task is being carried out in all 16 sites using nationally-available data.  For the most part, neighborhoods have been defined in terms of census tracts, and indicators are tracked in target neighborhoods and in comparison neighborhoods identified through cluster analysis of economic and social variables.  Construction of core neighborhood quality indicators has been guided by researcher assumptions about desirable low-income community features.

- The assessment task is being carried out in four impact sites using high-quality data from local sources.  (The sites are Indianapolis, Milwaukee, Rhode Island, and Twin Cities.)  Neighborhoods have been defined through a “bracketed matching” of candidate comparison neighborhoods in relation to target neighborhoods on a small number of critical variables. Indicators consist of a core set of national and common local indicators, selected to represent community features thought by researchers and local LISC staff to be desirable neighborhood conditions.  As the analysis unfolds, priority indicators that map to the goals and priorities outlined in community plans will be selected.

Section 3 describes the multiple types of data used in the analysis and how indicators of community change will be constructed from these data. National neighborhood data resides on a database constructed by LISC staff, drawing on all available Federal sources of local data.  Data for each of the four impact sites has been supplied and analyzed by local data warehouses that contain high-quality data on land use, property characteristics, crime, and other neighborhood characteristics.  The local data partners are:

- Indianapolis: The Polis Center at Indiana University Purdue University Indianapolis

- Milwaukee:  The Nonprofit Center of Milwaukee Neighborhood Data Center

- Rhode Island:  The Providence Plan

- Twin Cities: Center for Urban and Regional Affairs, University of Minnesota

Section 4 discusses the analysis approach to each of the monitoring and assessment tasks, emphasizing the importance of careful analysis of trends in analysis and comparison neighborhoods, including use of interrupted time series analysis.  Because of the variety of purposes to be served in the analysis, four different types of reports are being generated: annual assessment reports, neighborhood monitoring reports, topical reports and research papers, and methodological notes.

Section 5 outlines project organization, management, and work tasks, and discusses the emerging partnership between LISC and the Urban Institute’s National Neighborhood Indicators Partnership.

Supporting attachments can be found in a separate Appendix.  Numbered exhibits explicitly mentioned in the text are attached to the end of this document.

# 1.  Overview of the Sustainable Communities Initiative

Practitioners of community development have long recognized some of the systemic barriers to progress against problems of persistent, concentrated, poverty in American cities, and in the last several decades, a new generation of “comprehensive community initiatives,” has attempted to overcome or avoid these obstacles.   The Ford Foundation Neighborhoods and Families Initiative and the Annie E. Casey Foundation’s New Futures and Rebuilding Communities Initiatives, to name just two, aimed to solve problems of resource misdirection and fragmentation stemming from the specialized policy and program delivery systems important to neighborhood vitality.  They aimed to do so by creating the new structures of community empowerment and agency coordination needed to carry out programs comprehensively.

Funded by the Surdna Foundation and operating in the early- to mid-1990s, the Comprehensive Community Revitalization Program (CCRP) in New York City’s South Bronx was one of the most successful of these comprehensive initiatives.   The CCRP achieved dramatic results compared to previous efforts in similarly challenged neighborhoods, which spurred the MacArthur Foundation to carry out its New Communities Program (NCP) in Chicago, using Chicago LISC as its “managing intermediary” and drawing on the best elements of the earlier CCRP, including:

1.	The need for comprehensive interventions, responding to the multi-dimensional character of community well-being and the need to enlist, educate, and deploy multiple stakeholders and resource-providers in a planned, coordinated, effort to effect change.

2.	The primacy of community action and community-well being as the object of policy, in which citizen engagement, community-centered planning, geographic targeting, and sustained partnerships are foundational principles of programs and action.

3.	The criticality of accountability, in the form of institutional relationships and practices, designation of a lead agency, and the continuing flow of information on stakeholders’ performance and the outcomes of collective action.

From a small community-building program begun in 1995 and operating in three Chicago neighborhoods, the program expanded in 2003 to include 16 of the city’s low-income community areas.  Early analyses of the results of the New Communities Program point toward an unusually successful set of community outcomes and a strong, workable process for enlisting communities, agencies, and other systemic players as partners in a comprehensive effort.   Based on this experience, LISC staff and NCP practitioners developed a set of principles that capture critical aspects of the ruling philosophy and operating mechanics of the NCP.   (See Exhibit 2.)   These principles have been adopted by LISC to guide replication of the NCP experience into sixteen other LISC program areas.

Like other comprehensive community initiatives, the Sustainable Communities Initiative has an explicit place-based focus.  Communities are thought of in spatial terms – as people and institutions who share common interests and needs by virtue of their residence in proximity to one another.   Implicitly, the Initiative holds that some of the critical supports that individuals and families need are often found, or are best delivered, in places where people reside.  These features of communities have been formalized by NCP practitioners and LISC staff, based on decades of community development work in Chicago, as Key Characteristics of Sustainable Communities.  (See Exhibit 3.)

In general terms, these Key Characteristics represent a set of desired Sustainable Communities outcomes: the Initiative as a whole can be deemed a success if a significant number of the neighborhoods where this effort is carried out can be shown to make progress toward a state approaching that outlined in the Exhibit.   In terms of specific neighborhoods, however, organized communities articulate more concrete goals through their “quality of life” plans, which the programs identified in the plan aim to realize.  These more specific goals may pertain only to a subset of Sustainable Communities characteristics (although realizing them may trigger improvements in other areas that are not the explicit objects of policy.)

Measuring progress toward acquiring Sustainable Communities characteristics is one of the ten fundamental principles of the Initiative.  Measurement is important for several reasons: common information on community change has proven to be a good way to keep disparate parties engaged with one another; data and analysis support efforts to ensure accountability among the parties; and analysis results can support effective communications to supporters.  This information can come from a variety of sources, including qualitative data on major events, public perceptions, assessments of principal stakeholders and other sources.   It can also come from quantitative data, which because of its quality and scope can be analyzed in ways that produce more convincing evidence of program impacts than is possible using qualitative sources of information.

With the single exception of the Annie E. Casey Foundation’s Making Connections initiative, the accumulation and analysis of quantitative neighborhood information has not been a prominent part of earlier comprehensive initiatives.  In contrast, both the New Communities Program in Chicago and the Sustainable Communities program have accorded great weight to the assessment of neighborhood progress against the ultimate neighborhood change goals of the initiative.   As a result, the Sustainable Communities Assessment has invested considerable effort in the conceptualization of the quantitative, neighborhood change, portion of the analysis.

# 2.  Research Questions and Approach

The research serves two basic purposes: to monitor trends in target neighborhoods as the Initiative unfolds and assess whether the initiative has produced the changes sought. Each task has special requirements pertaining to indicator development, neighborhood comparisons, and spatial definitions of neighborhood.  The assessment task, in particular, places poses special informational, analytical, and operational challenges to this research.

## Analysis Questions

Overall, the assessment is guided by just a few general questions:

1.	Did target neighborhoods get better?  The research team constructed indicators for monitoring community trends in 16 sites using newly assembled data on community demographic, social, and economic conditions.

2.	What value did the Sustainable Communities initiative have?  Researchers will use statistical analysis of neighborhood indicators, in combination with qualitative analysis results, to determine whether observed changes can be credited, at least in part, to the Sustainable Communities account.

3.	How can revitalization efforts be carried out more effectively?  Throughout data collection, qualitative researchers in eight sites are collecting information on the successes and challenges of implementation.  They also will learn much of value to analysts carrying out the quantitative research.

The first question calls for analysis to monitor neighborhood change to inform local and national LISC staff and stakeholders about neighborhood progress, requiring development of a set of quantitative indicators tracking community conditions. Indicator selection was guided by theoretical understandings of neighborhood, informed in part by understandings of common community priorities in different types of low-income neighborhoods.

The second question calls for an assessment of the relationship between Sustainable Communities activities and community outcomes. This requires a complex effort to define neighborhood boundaries, develop comparisons across neighborhoods and time periods, marshal indicators, and analyze them in ways that result in convincing statements concerning the likely effectiveness of interventions.   Quantitative analysis will strive to test for statistically demonstrable differences the Sustainable Communities initiative made in community conditions.  (Qualitative researchers will carry out their own version of the analysis, drawing on both quantitative and qualitative data.)   Throughout this document, this analysis will be generally referred to as the “assessment of program effects” or “program assessment.”   Some of the analytical techniques to be used are commonly associated with community impact analysis; these will be used on a pilot basis in four sites to test whether local data and programs will support a statistically advanced impact study.

The third question will be answered by the qualitative analysts.  Qualitative researchers in eight sites are documenting program efforts, including approximate counts of units produced by priority community development activities, significant community events (such as the expansion of a local hospital), and participant evaluations of changes in community conditions, all of value to the quantitative portion of the analysis.

The process for carrying out the quantitative portion of the work will uncover issues linked to implementation of the initiative itself, which will be of value to the qualitative analysis; e.g., the analysis of concentrations of neighborhood changes that may help explain patterns of community conflict.

The monitoring and assessment analyses pose different requirements, but they are not isolated from one another.  To monitor neighborhood change, researchers have constructed a battery of core indicators of neighborhood quality and are tracking them in all 16 sites using national data sources and standard census geographies.  In the four impact communities, researchers are doing much the same, but as the program itself unfolds locally, researchers will tailor neighborhood indicators specifically to community quality-of-life plans, drawing on local data sources.  The national indicator development supports local assessment efforts, and the local indicator development supports national monitoring.   And national and local research efforts to examine the behavior of indicators over time should shed new light on the relationships among the multiple dimensions of neighborhoods.

## Characteristics of Neighborhoods

Analysis of neighborhood change necessarily simplifies an otherwise complex reality.  Neighborhoods can be thought of in terms of inter-related land, labor, and capital markets embedded within community institutions and relationships.  Neighborhood monitoring and assessment, however, relies on just a few highly abstract indicators of this complexity, and that said, even these few are not very well tested throughout previous research.

The items on the Key Characteristics of Sustainable Communities list are a strong beginning point for indicator development. The list comprises most of the outcomes likely to be found in community quality of life plans.  These characteristics can be grouped easily into the five domains of community quality embraced by the Sustainable Communities Initiative:  housing and real estate, income and wealth, economic activity, safe and healthy communities, and education.  Demographics has been added as a sixth category for analysis purposes.  (Demographics, by themselves, have no evaluative implications.)   These domains include:

- Demographics, including changes in the number of persons and households, and in the mix of types of households (family status and headship), ages, and races and ethnic groups represented;

- Housing and real estate, primarily including the mix of tenure, income groups, and affordability levels, housing quality, and the financial characteristics of housing in light of recent waves of subprime lending and related foreclosures;

- Economic Activity, including the performance of export-oriented sectors, access to high-quality retail, and transportation access to the broader city and region;

- Income and Wealth, principally including neighborhood employment, earnings, and reported income;

- Community Safety and Health , including public safety, physical attractiveness, effective delivery of basic urban services, and community institutions and relationships, and the availability of social and health Services to meet the needs of vulnerable members of the community; and

- Education and Culture, principally including high-quality educational opportunities for both children and adults.

## Development of Neighborhood Indicators

Neighborhood indicators are quantitative measures of community conditions that convey evaluative information, signaling welcome or unwelcome changes in community well being.  Good indicator development requires a series of explicit and documented judgments about five aspects: information quality, relevance, spatial resolution, interpretation, and evaluation.   Judgments according to each of these criteria tend to follow which of monitoring or assessment tasks is paramount.

First, information quality is problematic in most areas of social research, but especially so for aspects of neighborhood.   Generally, information on the operation of housing markets, such as property prices or mortgage transactions, is of good quality and readily available; data on employment and earnings has been historically weak but is getting better; data on public health at the neighborhood level is nearly non-existent.   For tracking change across all Sustainable Communities sites and target neighborhoods, these data are adequate to the kind of approximate judgments the monitoring task demands.  For assessing program effects, information from traditional sources contains debilitating flaws; the assessment task must rely primarily on alternative high-quality local data.  That said, one goal of this research is to validate national data by using them in combination with superior local information.

Second, from national sources of information, it is possible to construct a battery of national neighborhood indicators that taps, sometimes in very partial ways, in the six categories of neighborhood quality listed above.  These national indicators capture dimensions of neighborhood believed to be relevant to community concerns, although actual community preferences may not be known.  But without taking explicit account of community aspirations, it’s not clear how indicators should be “weighted” to arrive at an overall judgment of community progress.   In the four impact sites, local researchers can tie information directly to priorities outlined in community plans, using both national and local data sources to arrive at a group of indicators most appropriate to individual communities.

Third, neighborhood indicators come at different levels of spatial resolution.  At their most precise, indicators can be constructed from parcel level data, allowing advanced statistical analysis of spatial trends that closely match the location-specific goals of community plans.  Parcel level data are best able to support the analytical requirements of the assessment task. Census block group and tract data, at somewhat lower levels of spatial resolution, have been widely employed in neighborhood analyses, in part because boundaries were once drawn to produce areas of social and economic homogeneity, which in many cases they remain.   Zip-code level data has become increasingly available, but these geographies tend to be too large and heterogeneous to be useful for neighborhood analysis without extensive validation.

Fourth, interpretation of indicators is especially difficult in the community development context.  Sometimes the meaning of indicators is self-evident, as when crime rates go up or down.  (It is inconceivable that rising crime rates would be welcomed.)  In other instances, indicators have meaning only in the context of other neighborhood features, as when ordinarily desirable increases in homeownership are found to result from increased predatory lending.

Fifth, indicators are quantitative measures of community wellbeing.  As such, they are explicitly evaluative: improvements or decline in well-being must be judged relative to a standard of what counts as good or bad.  Sometimes, it is not at all clear how changes in an indicator should be evaluated; indeed, different residents in the same community may have different ideas of what would make their neighborhood better or worse, and judge an indicator accordingly.  And the very same change, as with property prices, might be welcomed by most in one neighborhood or decried by most in another depending on, say, the strength of local markets.

In this research, evaluative standards come from two basic sources: as set by analysts based on theory or by community residents based on values and interest. For the monitoring task, national researchers have assigned evaluative meaning based on statistical or other characterizations of community context and assumptions about typical preferences in lower-income communities; e.g., lower levels of crime, or more affordable housing.  The assessment portion of this research will rely on both types of standards: local researchers will develop indicators in light of local quality of life plans that declare community preferences, as informed by their own understandings of markets and communities.

To summarize: program assessment is best served by indicators constructed from parcel-level information available in real time to researchers able to respond to explicitly stated community priorities.  Because of the expense involved, this tailor-made approach is possible in only a few sites, especially since most of the data needed to carry out this analysis effectively are only available from local sources (which are not standard across localities).  Neighborhood monitoring makes some use of these indicators, as well, but because national data are available for some important dimensions of neighborhood quality, the monitoring task is being carried out across a larger number of cities and neighborhoods.

## Indicators Used to Monitor Changes in Neighborhood Quality

The field of neighborhood indicators development is no longer in its infancy.  Since the early 1990s, the National Neighborhood Indicators Partnership has supported construction of local data warehouses containing neighborhood level data used to engage community and civic leaders in efforts to track community well-being.   Earlier and continuing work using data from the decennial census also has introduced a number of neighborhood change measures into common use.  In 2007, LISC researchers canvassed the field and produced an inventory of 67 possible indicators covering most of the Sustainable Communities neighborhood dimensions.  (Each of these 67 can be further unpacked to yield still more indicators, producing hundreds of possible indicators.)

Researchers have used these candidate indicators as a beginning point for development of monitoring and assessment indicators.  These indicators have been developed without consultation with community leaders or reference to quality-of-life plans.  In advance of this work, however, researchers have produced a core set of neighborhood quality indicators covering the six neighborhood dimensions. These 30 indicators best satisfy tests of relevance, data quality, and neighborhood-level availability drawing from national and local sources.  (See Exhibit 4.)

Another distinction among indicators worth noting is whether they are indicators of population and household characteristics, in which measures are based on aggregated information about people and households within the analysis neighborhood boundaries, or whether they pertain to access, in which numbers of units and their distance from the analysis neighborhood are used to infer availability of a particular feature to residents; e.g., job access.  As the research progresses, analysts will explore other access measures, such as access to social and health services and transportation access.

## Construction of Comparison Neighborhoods

To determine whether neighborhoods are trending in the right direction, and further, whether programs may have had an effect, it is critical to match target investment neighborhoods against other similar neighborhoods that have not been so favored.   Different ways of defining comparison neighborhoods apply to the monitoring and assessment tasks:

- The monitoring task draws on data available from national sources to define a set of tracking indicators that are assumed to be relevant to community priorities.  Comparison neighborhoods will be identified through cluster analysis based on a set of variables thought to influence a range of possible outcomes.

- The assessment task draws on data available from local sources to customize indicators linked to priority outcomes outlined in community plans.  Multiple comparison neighborhoods have been constructed based on the similarity of their levels and trends on each of several priority outcome indicators.

### Selection of Comparison Areas for National Monitoring

Community leaders have a strong interest in knowing not just whether their neighborhood improved or declined, but how these trends compared to other neighborhoods.  Community leaders want to see homeownership rates go up, and the homeownership indicator may, indeed, be trending upward.  But homeownership may have increased in all neighborhoods, including the target neighborhood, in which case, the neighborhood cannot be said to be performing well with respect to the rate.  (Conversely, homeownership may have declined in the target neighborhood due to foreclosures, for example, but at a far shallower rate than was true of other comparison neighborhoods.)

The national monitoring data calls for a consistent method to be used to generate comparison areas in all 16 cities. While the characteristics of the comparison areas selected will vary by city, the methodology used to generate the comparison will be substantially the same.  Cluster analysis, a commonly used statistical method to group elements based on multiple shared characteristics, will be used to define comparison neighborhoods in each city.

Indicators Used

This set of indicators consists of variables that tap aspects of neighborhood likely to influence the future levels and pace of change in critical outcomes variables.  The following variables have been used in the cluster analyses to reflect housing values, tenure, stock quality, and racial composition and overall population change:

Exhibit 5

Variables Used in Cluster Analysis to Identify Comparison Areas for National Monitoring

| Variable | Definition |
| --- | --- |
| Housing value change | Proxied by percent change in HMDA median home purchase loan amount for single-family properties from 2000 – 2006. |
| Stock quality | Proxied using vacancy rates. Change in Census vacancy rates from 1990 to 2000 are the only source of vacancy rate data for the time period of interest. |
| Population Change | Percent change in population 1990 – 2000 from US Census, shown (in conjunction with change in poverty population) to produce useful groupings across all SC neighborhoods. |
| Racial and Ethnic Composition | Shown In multiple earlier analyses to be a driver of housing market clustering. Percent change from 1990 to 2000 for White Non-Hispanic, African-American Non-Hispanic, and Hispanic is used in most areas, reflecting the three dominant racial / ethnic groups in most neighborhoods. Asian-American is substituted for one of the groups noted where appropriate. Data are from US Census. |
| Poverty Rate | Percent of persons in poverty, 2000, from US Census |
| Majority Race | As with the racial / ethnic change variable, percent African-American is replaced when some other racial / ethnic group is dominant in the target neighborhood. |
| Renter Occupancy Rate | Percent of units occupied by renters, 2000, from US Census |

Cluster Analysis Method

The Ward method of cluster analysis (analysis of variables minimizing the sum of squares of any possible cluster) was used to assign census tracts to comparison groups. Only on low-income census tracts, defined in terms of household incomes that are at 80 percent of median or below, were included in the cluster analysis.  (Approaches that include all city tracts wind up devoting several of the resulting clusters to neighborhoods that have income and other characteristics that are obviously inappropriate for consideration as comparison areas.  Our approach to cluster analysis aims to discriminate in useful ways among low-income neighborhoods only.)

The cluster analysis was run separately in each site. The number of clusters used varied city-by-city depending on the best fit of the resulting clusters.  Cluster analysis results allowed each target neighborhood to be assigned to a cluster.  That cluster also contains tracts outside the target neighborhood which are designated as comparison neighborhoods.

Geography

Sustainable Communities target neighborhoods display a considerable range in population sizes, from highly compact areas of 1,300 people to broad areas containing upwards of 130,000 people.  In large target neighborhoods (and even in some smaller ones), program investments are likely to be concentrated spatially and their effects will be similarly concentrated.  In fact, some types of investments are likely to be concentrated in one area, other investments in other areas.   As a result, research staff encouraged local LISC program staff to identify these areas, which become the basis for neighborhood monitoring efforts.

Census tracts are the only ready-to-hand spatial unit that will allow identification of relatively compact areas within larger target areas.  (Zip-code level data are available, but in many instances will be too large to produce the desired spatial homogeneity.)  The monitoring analysis, therefore, uses census tracts to distinguish among sub-areas within target areas.

### Selection of Comparison Areas for Local Assessment

One of the most important goals of the Sustainable Communities Assessment is to determine whether the initiative gets results: do targeted neighborhoods change for the better compared to how they would change without it?    There are several ways to answer this question, most of them involving comparisons to other neighborhoods.  Ideally, these other, comparison, neighborhoods would resemble the target neighborhoods in all important respects except for the presence of projects, programs, and community capacities created by the initiative.

Methodology

The method used to identify comparison groups is a form of bracketed matching, using distances from the treatment neighborhood on multiple standardized variables.  This method was chosen because it gives researchers the greatest control over matching parameters, is easy to portray, explain, and revise, and permits creation of multiple comparison groups for multiple outcomes and related variables of interest.

Because we wanted to use multiple variables to make comparisons among tracts, we standardized each of the “level” variables using a simple z-scores, which take the range of values on any variable and converts it to a range with a mean of 0 and a standard deviation of 1.   Distances between any two values are expressed in terms of standard-deviation units.  This method allows us to declare that two cases x standard deviation units apart on one variable have the same relative distance from one another as two cases with the same number of units on another.   Once each of the seven variables had been transformed to its corresponding z-score, we adopted a range centered on the target case, within which the value of any case could be considered comparable to the target case.  This range was specified to allow approximately 7 – 10 tracts to emerge as possible comparisons for each neighborhood.

Indicators used

The analysis will rely primarily on three critical outcomes: house prices for single-unit properties, prices for 2-5 unit properties, and robberies.  House prices are generally thought to capture buyers’ relative valuation of neighborhood quality across neighborhoods and time; the assumption that neighborhood quality is capitalized into house prices has been extensively validated.  Robberies have been regarded by some as a bellwether of community safety threat conditions, and its use in comparison matching assumes that the target community will identify public safety as a very high-priority outcome.  (As the research proceeds, other outcome variables may become important to analyze, but the matching relies on these three.)

Exhibit 6

Variables Used in Cluster Analysis to Identify Comparison Areas for Local Assessments

| Variable | Definition |
| --- | --- |
| **Single-Unit Property Median Sales Price, 2005-2007 Average | Tract median sales prices for single-unit owner- or renter-occupied properties sold in 2005, 2006, and 2007. |
| **Trend in Single-Unit Property Median Sales Price 2005 -2007 |  |
| **Two-to-five Unit Property Median Sales Price, 2005-2007 Average | Tract median sales prices for 2-5 unit owner- or renter-occupied properties sold in 2005, 2006, and 2007. |
| **Trend in two-to-five Unit Property Median Sales Price 2005- 2007 |  |
| **Robberies per Thousand Population, 2005 – 2007 Average | Number of reported robberies / Census 2000 tract population |
| **Trend in Robberies per Thousand Population 2005, 2006, 2007 |  |
| Racial and ethnic minorities as percent of total population, 2000 | Census 2000 total Hispanic and African-American population /Total tract population. |
| Percent housing units that are owner-occupied, 2006 | Number of owner-occupied parcels, 2006 / Total number of residential parcels, from city parcel-level data. |
| Median Family Income, 1999 | Census 2000 tract median family income, 1999. |
| Crude Birth Rate, 2007 | Department of Health total number of live births in 2007 / Census 2000 total tract population |

**Denotes level and trend of outcome variables

Note that each outcome is measured by a “level” and “trend” variable.   These variables act as pre-tests for the outcome variables used in the post-test comparisons.  In the analysis to follow, once tract matches to tract 19 have been identified for the level variables, they are further screened on the three trend variables.  For example, neighborhoods that match on price levels are screened to ensure that prices prior to the baseline year are trending in the same direction.

The remaining variables have been chosen because they are thought to influence relative levels and trends on the pretest / outcome variables, and otherwise influence the relative effectiveness of interventions.   Owner-occupancy has been linked to civic participation as well as stability of residential tenure; minority population is tied to housing market performance (including the volume and type of home mortgages available) and is a proxy for other attributes of areas of concentrated disadvantage; median income is tied to a series of health, education, and employment outcomes; and crude birth rate is a measure of neighborhood lifecycle.

It likely that as the initiative unfolds in the impact sites, specific neighborhood quality-of-life plan goals will take on paramount importance compared to others.  This argues for development of separate comparison areas for each indicator because there are no assurances that neighborhoods that are similar on the indicators listed above would prove to be similar in all other respects.   While it may be impractical or unwieldy to do this for a large number of indicators, it can be done easily for three or four high-priority ones.   This option will be explored if warranted by local circumstances.

Geography

The same problem of heterogeneous neighborhoods encountered in the cluster analysis approach to comparison neighborhood identification surfaces as well in the bracketed matching approach.  Especially in sites where Sustainable Communities neighborhoods are quite large – Twin Cities and Indianapolis – neighborhoods prove to consist of distinct sub-neighborhoods that display very different profiles on the indicators used to construct comparisons.   In these instances, the bracketed matching approach did produce useful sets of comparisons, but effecting the matches proved cumbersome.

In the impact sites, the local data partners will generate data that are available at the parcel level.  In order to use these rich data to assess whether progress is being made in target neighborhoods across different types of outcomes, comparison areas may be constructed for each of several types of outcomes.  This may be most clearly warranted for analysis of crime levels and trends, which are highly localized within the census tracts used for target and comparison neighborhood boundaries.

## Baselines to Compare Pre- and Post-Intervention Indicator Levels and Trends

The assessment task requires careful comparison of changes in the levels and trends in outcomes indicators prior to introduction of the Sustainable Communities Initiative (the “pre-intervention” period) and afterwards (the “post-intervention” period).  In the best case, interventions would occur in all “treatment” neighborhoods at a single point in time.  In the Sustainable Communities case, interventions are staggered even within one city, often rolled out over a number of years.

These aspects of the initiative make it difficult to define clear pre- and post-initiative periods for purposes of analysis.   One solution from earlier research on community development impacts was to define an “interim” period between the pre- and post-periods to allow for extended times during which projects were under development.  An analogous interim period to accommodate community quality of life planning or early action projects prior to initiation of major investment activities may be necessary in defining baselines for this analysis.   These pre-, post-, and interim-periods will be defined case by case for all sites and neighborhoods in the assessment and monitoring efforts.

Moreover, some programs and activities have been in place before a neighborhood’s designation as a Sustainable Communities target area.   For assessment purposes, the relative levels and trends of outcome variables among target and comparison neighborhoods should account for these previous and continuing effects.  Nevertheless, there remains a policy and research interest in estimating, however approximately, the effects of previous investments on the neighborhood over a more extended period prior to the SC initiative, allowing researchers to take advantage of the considerable amount of data assembled for this project.  This means creation of a “secondary baseline” tied to the approximate year(s) of initiation of major community development efforts, which might be sometime between 1990 and 2007.   As part of their work, local LISC staff and qualitative analysts will supply dates for the baseline and secondary baseline to quantitative research staff.

# 3.  Summary of Data Sources, Uses, and Analysis Samples

## National Neighborhood Monitoring Database

Neighborhood indicators are constructed from data supplied by national and local sources.

National data, typically from Federal sources, are rapidly increasing in quality, coverage, and currency, but there remains considerable variation across sources in level of spatial resolution, the length of time series that can be constructed, and currency.  Most of these data, as well, must be re-purposed to allow their use as indicators of community development-related conditions.  For example, United States Postal Service collects data on addresses and occupancy to help it deliver mail, but these data also have promise as indicators of long-term vacancies, important to community developers.  These and other databases form an analysis asset of considerable value to the assessment and to LISC’s overall operations.

LISC Research and Assessment has created a national neighborhood monitoring database that houses nearly all available Federal data on neighborhoods at the zipcode level and below, drawn from various Federal agencies, including:  the US Census, Internal Revenue Service, United State Postal Service, Department of Commerce, Office of the Comptroller of the Currency, and Department of Education.   Providers, source files, and principal variables are shown on Exhibit 7.

Indicators drawn from the sources shown on the exhibit are essential for monitoring neighborhood change across all sites and neighborhoods.  Some of these data have entered into common use; HMDA data, for example, have been used in countless studies of mortgage lending patterns, and in recent years, have been critical to the latest generation of neighborhood impact analyses.   Other data have only recently become available, and are untested.  An important contribution of this project will be validation of new sources of neighborhood change data through both the monitoring and assessment tasks, in which national data are used in conjunction with local data to describe and assess neighborhood change.

Although the primary value of the national data is to allow monitoring of neighborhood change over many communities and neighborhoods, some national sources of data also can be used for program assessment purposes; for example, property prices can only be obtained from local data; mortgage information, such as the race of borrowers, can only be gotten from national sources.  Both are useful indicators of change in housing markets for the purpose of assessing program effects.   Further, some local indicators will be helpful for national neighborhood monitoring purposes, even though they will be available only for a four-site subset of communities.

## Local Neighborhood Indicator Systems

Local neighborhood indicator systems are critical assets to assessing program effects because they contain information – on property characteristics and crime incident locations, for example – that are important to neighborhood quality and not available from any other source.  Often, these data are available in real time or at frequent intervals, allowing analysts to construct the time series’ needed to carry out good trend analysis, as well as depict current conditions.

These systems are constructed, maintained, and improved at considerable expense by analysts from local “data warehouses.”  Unlike national data sources, these systems cover only the cities, counties, and sometimes states they are located in.  Because jurisdictions vary greatly in the legal, regulatory, and administrative systems they have devised to tax properties, grant permits for construction, fight crime, and carry out other governmental functions, the data these systems generate are similarly varied.

This variation has several consequences.  It is difficult to combine data from different jurisdictions for the purpose of carrying out joint analyses.  It is also difficult for analysts unaccustomed to working with specific local databases to manipulate and analyze their contents.  This means that use of local indicators for national assessment work is best carried out through cooperative efforts of national researchers and local analysts, and in only a few sites because of the difficulty and expense involved.

Exhibit 8 lists the data elements in each of six neighborhood dimensions that are available from at least two of the local data warehouses in the impact sites and from national sources, including dates available and degree of spatial resolution.  The exhibit illustrates the considerable advantage over national data of having local information common to both local sources, including availability of property sales and property characteristics at the parcel level, and data on vacant and abandoned property, crime, and births and deaths.  Other data are available from one or the other source on property foreclosures, labor force participation, nonprofit organizations and facilities locations, and other variables.  It’s worth noting that even with the contribution of these local data, indicator coverage remains weak in several neighborhood categories, most notably community institutions and relationships and social and health services.

The core set of neighborhood quality indicators, introduced in a previous exhibit, have been drawn from data supplied by the national data set as well as common data items contributed by the local data warehouses.   Exhibit 4 provided further information on these indicators, including years available, the data source, and whether they are available in all sites, or in the impact sites only.   It is likely that this list will expand as local data partners expand their information inventory, in part using support provided by this research project.

## Analysis Samples

Because of the difficulty and expense involved in carrying out monitoring and assessment tasks well, not all of the 16 Sustainable Communities sites and 47 target neighborhoods will be included in the analysis in exactly the same way.  The various samples in the analysis and their specific treatment include:

- All 16 Sustainable Communities sites will be included in the monitoring analysis carried out by national research staff, using information from the National Monitoring Database.   This involves an annual report for national reporting purposes (which will include Chicago) summarizing changes across sites and neighborhoods, as well as individual reports for each neighborhood.  (Names of target neighborhoods can be found in Exhibit 9.)

- Four impact Sites, including Rhode Island, Milwaukee, Twin Cities, and Indianapolis, are included in the assessment of program effects, which draws on data from both national and local neighborhood information systems.  In addition, local data is included in annual monitoring reports prepared by national and local staff.  These sites were selected based on:  (a) the degree to which the program design reflects Sustainable Communities principles; (b) the timing and scale of the interventions; and (c) availability of high-quality local neighborhood information;

- Analysis neighborhoods, including 13 neighborhoods selected from among 33 target neighborhoods in 8 selected sites – four impact sites and four non-impact sites, based on the quality of the local program design, intervention timing, prospective strength of the intervention relative to previous community-building efforts and size of target area, and expected cooperation from community stakeholders in the qualitative portion of the study.  (Names of analysis neighborhoods also can be found in Exhibit 9.)

- Assessment Comparison Neighborhoods, in the four impact sites drawn based on their similarity to analysis neighborhoods on the level and trends of critical outcome variables prior to inception of the Sustainable Communities program.

- Monitoring Comparison Neighborhoods in all 16 sites, drawn based on their similarity in social and economic status to analysis neighborhoods as shown by cluster analysis.

# 4.  Analysis and Reporting

## Analysis Strategy

All social science learning depends on comparisons of similarities and differences across groups.   In this analysis, comparisons of similarities and differences are possible across sites and neighborhoods and up and down levels of analysis, which range from systems at the most general level of analysis to parts of communities at the most specific level:

- Systems are the inter-related people and institutions that mobilize money, expertise and political support to sustain and strengthen communities.  Systems display differences primarily in the volume of resource flows and the relationships among institutions.

- Communities are defined by their demographic, social, economic, cultural, and institutional characteristics; and

- Constituent Elements of Communities include important sectoral and spatial distinctions within communities.

Analysis makes use of similarities and differences across communities and levels of analysis to isolate the effects of specific community change efforts.  For example, detectable differences in crime rates across otherwise similar target and comparison communities may support claims that SC initiatives have produced the observed differences.  Similarities in community conditions across very different systems may help rule out systemic explanations of changes observed across communities within a single system.

The monitoring analysis requires fairly straightforward comparisons across neighborhoods within and across sites.  The data collection and indicator construction effort produced longitudinal data files on change at the neighborhood level for all target neighborhoods in the 16 Sustainable Communities sites.   Statistical analysis has classified all low-income neighborhoods through a cluster analysis of important social and economic variables.  In the baseline reporting already completed, analysts have compared target neighborhoods on selected variables to all other low-income neighborhoods in each site using readily available census and HMDA data.   In the first annual report on the program, the monitoring analysis covering the entire portfolio of sites and target neighborhoods prepared for national LISC and other national audiences will:

- Construct time series’ for the core neighborhood quality indicators, drawing on national data and selected local data from the impact sites for analysis and comparison neighborhoods.

- Identify important systemic characteristics of the sites, using such variables as metropolitan area house prices, employment and income, and other measures and classify areas according to their relative performance.  These classifications will be used to analyze differences in neighborhood trends across sites.

- Compare the levels and trends of each core quality indicator in target neighborhoods to neighborhoods in the appropriate comparison group (or cluster).   This comparison will identify neighborhoods that appear to conform to, and deviate from, the overall pattern established by the group.

- If possible, project changes in target and comparison neighborhood based on recent trends to establish performance benchmarks for each neighborhood in absolute terms and relative to neighborhoods in the appropriate comparison group.

In later years, changes in neighborhood values on individual indicators and groups of indicators relative to established trends for each neighborhood will be taken as indicative of possible program effects.  These neighborhoods will merit closer attention in subsequent quantitative and qualitative analysis.  It should be emphasized that given the imprecision of the comparisons and lags in critical variables, results are indicative, not conclusive.

In addition to the national monitoring analysis, neighborhood monitoring reports have been prepared for each neighborhood (in highly summarized form) and for each site.  (These will be distributed to sites in the winter of 2010.)

The assessment of program effects is similar in some respects to the monitoring analysis just outlined, but with important differences pertaining to more relevant and timely data, precise neighborhood comparisons, and correspondingly flexible neighborhood boundaries. These will allow more exact and timely analysis of target and analysis neighborhood changes than is possible to do in the monitoring analysis.  In addition:

- The increased level of precision made possible using local data will allow the careful specification of pre- post- and interim-periods needed to carry out statistical analysis of possible program effects.

- Import of data on timing, levels, and types of investments, programs, activities and critical economic, social and political events from the qualitative analysis will allow specification of pre- post- and interim periods, and contribute explanatory / interpretive data on how effects were produced.

- Interrupted time series analysis will be used to determine whether the levels and trends of outcome variables in target neighborhoods display statistical differences from those prevailing in comparison neighborhood both before and after implementation of Sustainable Communities programs.

It should be acknowledged that the statistical bar set by interrupted time series methodology is quite high and that the ideal conditions for its use – geographically concentrated investments, clear pre- and post-intervention periods, availability of accurate data over an extended period of time – do not often present themselves.  For these reasons, assessments of program effects will not rest entirely on the quantitative analysis, but will also be informed by the expert judgments of community and systems-level stakeholders and other high-quality evidence.

## Reports

The content and format of reports written for the Sustainable Communities Assessment will be shaped by the need to meet the knowledge-sharing needs of audiences internal and external to LISC, support implementation in each site, and back LISC exercise of leadership in the community development field.   Different types of products are required to communicate results from different types of analyses, respond to the needs of different audiences, and pursue the following purposes:

- Accountability of national and local LISC for results from the considerable investments made in this approach to community change.  The quantitative analysis contributes to this by carrying out a rigorous assessment of results, and communicating these to the LISC board and funders through the annual national assessment reports and local neighborhood monitoring reports.

- Accountability of community partners and contributions to Sustainable Communities implementation efforts through creation of a core set of common neighborhood performance information.   These are communicated to local practitioners through the annual neighborhood monitoring reports.

- Development and testing of new monitoring and assessment methods, including construction of new or improved indicators across a number of neighborhood dimensions and validation of national data used to track neighborhood change.  Examples include the use of HMDA data on mortgage borrowers to monitor neighborhood racial and ethnic change and use of voting participation data as a proxy for community strength. These findings will be communicated to other researchers and research funders through methodological notes and reports on specific neighborhood change topics.

- Development of new understandings of neighborhood dynamics based on careful comparisons across neighborhoods and systems using high-quality data and drawing on the collaborative work of national and local experts in neighborhood change analysis.   These results will be communicated to researchers and policymakers through topical reports and research papers.

- Knowledge contributions to the community development field as a whole through cross-site assessments of the value of Sustainable Communities interventions as shown in both quantitative and qualitative analyses, and communicated through both the topical reports and national assessment reports.

Each of these types of reports relies on different combinations of indicators available from multiple sources.  A map of indicators to uses is provided at Exhibit 10.

# 5.  Management and Workplan

## Project Organization

The organization of the assessment is complex, reflecting the national and local character of the work and the combination of qualitative and quantitative approaches.   An organizational chart is shown in Exhibit 10.   A description of responsibilities for each actor in the organization chart can be found at Attachment 1 and a short description of selected named individuals and institutions can be found in Attachment 2.

The LISC Director of Research retains overall responsibility for the design of the research, implementation direction, and synthesis and communication of the findings.  Internal support for operations and analysis is provided by a Project Manager, responsible for operational direction, and a Research Associate, responsible for construction of the National Monitoring Database and analysis of the data it contains.

The core research team is advised by an internal Assessment Committee, guided by senior LISC national staff responsible for Sustainable Communities Program implementation, field operations, and policy.

The local site teams consist of research partners to carry out the qualitative portion of the work, and in the four impact sites, data partners to carry out the quantitative portion.   By necessity, data partners are locally based, as are the qualitative researchers, enabling them to track developments throughout the year and arrange interviews to suit participant schedules.

The quantitative and qualitative researchers have roughly parallel scopes of work.  Because the national research design cannot easily anticipate the considerable variation in local environments, objectives, programs, and sources of data, local researchers’ first major task was to prepare an analysis plan that adapted the national design to local circumstances.   Each developed a baseline report on community conditions, which for qualitative researchers treated the objectives, relationships, and resources of important community and system actors.   Each delivers annual reports of findings.

In the impact sites, these analysts will be expected to coordinate their work to some degree, but each of research and data partners have independently prepared local analysis plans, collected data and analyze them, and reported on findings.  The reporting schedule has been staggered to enable quantitative data analysts to complete their work and contribute results to the qualitative analysis still underway.   Qualitative researchers are expected to take account of, and help interpret the meaning of quantitative findings as they prepare their reports.

The success of the initiative rests largely with the leadership, expertise, and financial resources mobilized by local LISC staff.   They have major stake in the investment, and therefore have carried great weight in national staff decisions on the content and timing of consultant work scopes.  They are also an important audience for the results.  It should be emphasized that although the research will be valuable to them, the primary audiences for the research are national.   Local staff have been given an opportunity to comment on the draft reports, but the final say on content and interpretation remains with national research staff.

In the development of this plan and initial deployment of consultants, LISC staff have been helpful in the effort to identify analysis neighborhood and identify suitable research and data partners.  As the research unfolded, they where asked to request that lead agencies cooperate with the assessment, introduce the local research consultants or teams to principal partners, and participate in determining research priorities for the site. LISC staff in both impact and non-impact sites will have the option of extending data collection over the core requirement, to be worked out case-by-case when the national design is adapted for use in each site.   In several sites, they have contributed funds for locally-specified additions to the core national research design.  (Oversight of “supplemental” analyses paid for at local option has been exercised locally.)

## Communication and Collaboration

The research requires cooperative efforts from LISC national and local staff, quantitative and qualitative researchers, and national consultants and advisors.   One of the reasons why LISC designated a full-time project manager to the work is to ensure that the appropriate attention be given the coordination of these various efforts.   Particularly important is the need to ensure that local research product delivery schedules mesh with the timing of national report preparation, and that changes and adaptations to the research design as the work progresses are reconciled with one another and duly communicated to researchers.

In addition to active management of the process, several other ways to coordinate the research include:

- Circulation of interim work products among the consultants and advisors in the project.

Each year, qualitative consultants produce research material of considerable interest to the other researchers.  Quantitative researchers have carried out data reconnaissance early in the research process, developed analysis plans to state how indicators will be constructed in response to local priorities and available data, and prepared neighborhood monitoring reports.  Each of these documents, shared among the four impact site research teams, has helped stimulate adoption of promising ideas throughout the group.

- Convenings of research consultants at critical points in the research.

The national research team has separately convened in-person gatherings of the qualitative and quantitative researchers each year.   Quantitative researchers convened at a point when each team had carried out most of its local responsibilities to share ideas about indicator construction, comparison neighborhood identification, and analysis issues.   The qualitative team convened after baseline or first annual reports had been completed.  Researchers shared early findings for individual sites, suggested specific lines of inquiry for the national analysis, and highlighted areas for intensive focus in the next year’s data collection.

- Electronic collaboration to share or create research products

Work carried out by the quantitative researchers has displayed considerable overlap in terms of types of data, neighborhood change priorities, and appropriate methodologies for indicator construction, neighborhood boundary definitions, and other technical tasks.   This circumstance has favored close collaborative work enabled by new forms of electronic communication.

The Nonprofit Data Center in Milwaukee has been using wiki technology for several years to aid in collaborative proposal writing, file sharing, and content generation.   This wiki site has been used to critique this analysis plan and extend portions of it as joint research products.  For example, the comparison neighborhood selection strategy outlined in this document is the outcome of considerable thought and detailing among the partners.  It is also likely that other researchers in the field would benefit from understanding the methods pursued here.

## National Partnerships

The research team is mindful of the value this assessment will have to the community development field, and the potential contributions others may make to help realize the objectives of the research.  For this reason, partnerships with other national organizations will be important to engaging others in this work.  Two relationships in particular have emerged at an early stage as valuable as the data collection and analysis strategy unfolds, and a third set of partnerships is likely to form as well:

- The National Neighborhood Indicators Partnership (NNIP) housed at the Urban Institute has become the foremost national center of support for the accumulation and use of data on community change.  The four data partners in the impact sites are prominent members of NNIP.   The relationship with NNIP has proven valuable in several respects: NNIP provides a forum for the introduction, discussion, and improvement of methodologies developed in this research; it allows the research team access to experts in indicator development and use in specific content areas; e.g., analysis of crime patterns.

- The Success Measures Project housed at Neighborworks America has developed evaluation methodologies tailored to the specific interests and capabilities of community development corporations and other community-based nonprofits.   In several sites, organizations that have been designated as lead agencies under the Sustainable Communities initiative also are pursuing Success Measures projects.  These data gathering and analysis activities complement the work being carried out by local qualitative and quantitative researchers.  LISC and Success Measures Project staff have begun to explore ways to take full advantage of this overlap in research activities in Twin Cities, Milwaukee, and Detroit.

- By virtue of its comprehensive approach, the Sustainable Communities initiative, and the assessment as well, will touch on a number of policy domains that have created their own research concepts, methods, and findings.  Some of these bear directly on place- and community-centered approaches, including such fields as community policing, public health, and communities and schools.  It is likely that as indicators are developed, tested, and analyzed in each of these fields, it would be advantageous to forge relationships with organizations active in these areas.

## Work Tasks and Schedule

Implementing the Sustainable Communities assessment has required coordinated national and local efforts across 16 sites and some number of neighborhoods.   Many workplan details will continue to be worked out as the assessment unfolds.  Attachment 3 outlines the major tasks carried out by national staff,  staff working on the National Neighborhood Monitoring Database, and local data partners as the assessment unfolded over its first year.

Exhibit 1

Summary of Approach to Monitoring and Assessment Tasks

|  | Monitoring | Assessment |
| --- | --- | --- |
| Primary Purposes | Track neighborhood conditions and analyze trends compared to peer neighborhoods | Analyze comparative performance to assess effects of Sustainable Communities programs |
| Coverage | Sixteen sites and 47 neighborhoods, with special attention to 13 analysis neighborhoods | Four sites and eight (of the 13) analysis neighborhoods |
| Sources of Data | National data for 16 sites, supplemented by selected items from four pilot sites | Local neighborhood indicator systems supplemented by selected variables from national sources |
| Evaluative Standards | Derived from theoretical assumptions about neighborhood change and assumed preferences of low-income residents | Derived from goals and priorities outlined in community plans, supplemented by researcher understandings of neighborhood dynamics |
| Comparison Neighborhoods | Selected through cluster analysis of social and economic variables thought to influence program outcomes. | Selected by bracketed matching of levels and trends of outcome variables. |
| Spatial Analysis | Use census tracts as smallest unit of neighborhood analysis, aggregated to form homogeneous sub-neighborhoods within target areas | Use parcels and spatial statistics to identify areas of homogeneity within target areas, used to identify sub-neighborhoods. |
| Reporting | National neighborhood monitoring reports for each target neighborhood and national assessment report. | Local monitoring reports and national assessment report |

Exhibit 2

Key Principles of Sustainable Communities

- Neighborhood/community planning.  Sustainable Communities activities should be rooted in a local plan that is the result of inclusive engagements of residents and other key local stakeholders.  The plan should reflect a community’s vision, goals, and priorities.

- Community engagement.  An initial and ongoing set of organizing activities that can serve as a consistent form of input and engagement with the community is essential.  That engagement is woven through neighborhood/community planning and design processes as well as eventual implementation activities.

- A comprehensive array of development activities.  A range of strategies/approaches that are rooted in the neighborhood/community process and encompass several or all of the following programmatic objectives must exist: expanding capital investment in housing and other real estate; increasing family income and wealth; stimulating local economic activity and connections to regional economies and beyond; improving access to quality education; and supporting healthy environments and lifestyles.

- Geographic targeting on one or more neighborhoods, communities or particular sub-areas within them that provides a focus for the resources and efforts of the sustainable communities initiative.

- Neighborhood lead agency.  An entity should be designated to anchor the comprehensive effort -- to be accountable for the Sustainable Communities work in a given neighborhood.

- Existence of a strong civic partnership-- local buy-in and meaningful engagement of funders, local government, CDCs, LISC staff and LAC and other key partners.  The local program’s ability to raise additional dollars, in particular, from new and existing funding sources, both private and public, will be especially important.

- Means of measuring progress & impact at the community level.  Measuring progress should have both a qualitative and quantitative dimension.

- Intensive, on-going communications activities.  This is multi-faceted, ranging from the use of journalists in documenting and telling the story of the community process, to assuring that the effort has a common message and brand, to having ample publicity in order to engage interested parties, attract more resources, help build momentum, and provide lessons for the broader field.

- Accountability.  There must be accountability at every level -- e.g., for LISC, lead agencies and other neighborhood actors, including CDCs, consultants, funders, city officials, etc.  This cannot be ad hoc; it should be built into the program model.

- Brokering & negotiating skills.  LISC staff and partners must utilize a new set of skills rooted in brokering and negotiating roles.  The ability to manage process, convene partners and communicate differently are essential to building successful comprehensive community development models.

Exhibit 3

Key Characteristics of Sustainable Communities

- They offer a variety of housing options that respond to a diverse market of homebuyers and renters of different income levels; they also are places that recognize the value of preserving housing that is affordable for households of limited means.

- They are economic contributors to their broader regions, by producing goods and services that are needed, providing a workforce to support the regional economy, and providing residential opportunities for people who work nearby.

- They have strong local institutions – for example, community-based organizations, other nonprofits, larger anchor institutions such as colleges, hospitals and larger private employers – that help to build social capital and relationships within and beyond their boundaries and that add value by contributing ideas and resources to address local problems.

- They are communities that nurture new leadership, by strengthening resident capacities -- especially of lower-income families, recent immigrants and youth – to ensure their involvement in shaping the future of the community.

- They have attractive physical amenities likes parks, open spaces, recreational facilities and other physical infrastructure that contribute to good quality of life. They are safe places where residents and visitors can move about without fear of crime and violence.

- They are publicly well served communities with high quality public services, such as street cleaning, garbage pick-up, and lighting.

- They are caring communities that offer opportunities for childcare, youth development, health and wellness, and social services for special needs populations.

- They are smart communities, with schools that deliver quality education for children and educational opportunities for adults that are working or want to work or that may no longer work but are interested in opportunities for lifelong learning. The goal is to equip residents to participate in the economic mainstream.

- They are technologically connected to the wider region and the world, where residents have affordable access to the Internet to provide critical connections and services that enable residents to earn, save, learn, and build assets.

- They offer opportunities to work in upwardly mobile jobs in the community or in locations easily accessible through public transportation.

- They are creative communities that offer arts and cultural opportunities in the community or nearby.

- They offer high quality shopping in the community or easily accessible nearby.

- They are physically connected to the wider region through transportation options that make movement in and out easy and affordable.

Source:  Local Initiatives Support Corporation, Strategic Plan 2006-20010, November 2005.

Exhibit 9

Sites, Cities, Target Neighborhoods and Analysis Neighborhoods in Sustainable Communities Sites

| SC Site | Neighborhood | Analysis Neighborhood |
| --- | --- | --- |
| Bay Area (San Francisco, Richmond) | Chinatown (SF) | Nystrom (Richmond) – projected |
|  | Nystrom (Richmond) |  |
|  | Excelsior (SF) |  |
| Detroit | Central Woodward | Southwest (Springwells Village) |
|  | East/Near East |  |
|  | Northwest |  |
|  | Southwest |  |
|  | Northeast |  |
| Duluth | Central Hillside | Central Hillside Lincoln Park |
|  | East Hillside |  |
|  | Lincoln Park |  |
|  | Morgan Park |  |
|  | West Duluth |  |
| Indianapolis | Binford /Northeast | Near Eastside (Near East) Southwest (West Indianapolis) |
|  | Crooked Creek/Northwest |  |
|  | Near Eastside |  |
|  | Near Westside |  |
|  | Southeast |  |
|  | West Indianapolis / Southwest |  |
| Kansas City (Kansas City, KA, Kansas City, MO) | St. Peter Waterway (KA) | Downtown Kansas City, KA Ivanhoe Northwest |
|  | Downtown KCK (KA) |  |
|  | Blue Hills (MO) |  |
|  | Douglass-Sumner (KA) |  |
|  | Ivanhoe Northwest (MO) |  |
|  | Scarritt Renaissance (MO) |  |
| Milwaukee | Washington Park | Harambee |
|  | Harambee |  |
| Rhode Island (Providence, Woonsockett) | Olneyville (Providence) | Olneyville Woonsockett |
|  | Woonsockett “sub-neighborhoods of Fairmont Constitution Hill and Main Street Riverfront |  |
| Twin Cities (Minneapolis, St. Paul, Hopkins) | North Minneapolis | Central Corridor North Minneapolis |
|  | St. Paul Central Corridor |  |
|  | St. Paul Eastside |  |
|  | South Minneapolis |  |
|  | Hopkins |  |
| Washington DC | Congress Heights |  |
|  | Southwest |  |
| Rural Pennsylvania | Uniontown |  |
|  | Tamaqua |  |
| Chicago | Auburn Gresham |  |
|  | Chicago Lawn |  |
|  | Douglas, Grand Boulevard, North Kenwood-Oakland |  |
|  | East Garfield |  |
|  | Englewood |  |
|  | West Haven (Near West Side) |  |
|  | Humboldt Park |  |
|  | Logan Square |  |
|  | Pilsen (Lower West Side) |  |
|  | North Lawndale |  |
|  | South Chicago |  |
|  | Little Village (South Lawndale) |  |
|  | Washington Park |  |
|  | Woodlawn |  |
| San Diego | Conlina Park / City Heights |  |
|  | Logan Heights / Barrio Logan |  |
| Philadelphia | West Philadelphia |  |
| Houston | Near Northside |  |
|  | Independence Heights |  |
| Mid-South Delta | Greenville, MS; Mariana, AR |  |
| New York City | Not yet Determined |  |
| Newark | Orange (Valley) |  |
|  | Lower Broadway |  |
|  | Kent/Brenner/Springfield (Central Ward and South Ward) |  |

Sites and Neighborhoods as of November, 2009.  The table Includes 63 neighborhoods: 47 neighborhoods in 16 Sustainable Communities cities and 16 Community Areas in the Chicago New Communities Program.

SUSTAINABLE COMMUNITIES

QUANTIATIVE ANALYSIS PLAN ATTACHMENTS

1.	Responsibilities of SC Assessment Participants

2.	Capabilities of Research Team and Partners

3.	First Year Sustainable Communities Workplan

Attachment 1

Responsibilities of LISC Sustainable Communities Assessment Participants

National Assessment Committee:  Consists of senior LISC managers and select local program directors, convened to advise the research team on: (1) relationships to the national implementation process; (2) other relationships with the LISC field; and (3) the value of assessment products and results to LISC national objectives.

National LISC Research and Assessment:  Direct research and ensure research product quality and suitability for LISC program, policy and communications efforts.  Principal activities include: (1) oversee national research consultants and program manager; (2) create research design and project management plan; (3) participate in SC skill building activities; e.g., learning forums; (4) construct and use national indicators of neighborhood change in demonstration and pilot sites; (5) participate in pilot site impact analysis; and (6) lead drafting of national project reports.

National Research Consultants:  Small consulting team to provide support in: (1) collection and analysis of qualitative process, outcomes, and impacts data in cooperation with local research partners in Pilot sites; and (2) collection and analysis of quantitative data on program impacts in Pilot sites.  The national research consultant will participate in design and assessment activities.

Project Manager:  LISC research associate assigned to coordinate and manage the SC performance assessment process, including monitoring activities across sites, coordinating logistics, tracking expenditures and status of deliverables.

LISC Program Director:  Responsible for advising the local impact assessment design and data collection effort, helping gain access to data sources, and consulting on the form, content, and uses of local evaluation reports.

Local Research Consultant (Demonstration Sites): Carry out process and production data collection from archival material and interviews, and readily obtainable quantitative data from local management systems.  Prepare local project research reports. Coordinate with local LISC staff and national implementation consultants.  Supply research to local journalists.  Work at the direction of national research consultant and program manager

Local Research Partner (Pilot Sites): Conduct process and outcomes data collection similar to sites, but with:  (1) intensive focus on target neighborhoods and comparison neighborhoods, (2) a broader range of archival, interview and quantitative data collection activities on program  impacts, and (3) use of high-level quantitative information on neighborhood change.  Carry out interviews and coordinate data collection with national research consultant and program manager.

Local Data Partner (Pilot Sites) Acquire quantitative data on neighborhood change from local sources and assemble analysis databases for use by national assessment staff.

Attachment 2

Sustainable Communities Initiative Assessment –

Description of Research Team and Partners

LISC RESEARCH STAFF

Chris Walker

Research Director

Chris Walker is Director of Research and Assessment for the Local Initiatives Support Corporation, the nation’s foremost community development intermediary.  He is responsible for assembling, conducting, sponsoring, and disseminating high-quality research on community development’s contributions to the well-being of individuals, families and communities.    He also supports the research activities of the 30 LISC local programs throughout the United States.  Currently, he directs the assessment of LISC’s new comprehensive community change initiative, and is studying the impact of low-income housing tax credit projects on neighborhoods and families.  He also provides senior research support to LISC-MetroEdge – an analysis and community consulting practice devoted to uncovering hidden retail potential in low-income urban neighborhoods.

Prior to joining LISC in late 2005, Mr. Walker was director of the community and economic development program of the Urban Institute in Washington, DC, where he worked for 19 years.  His research at the Urban Institute included national studies of federal- and foundation-funded affordable housing, community lending, small business development, cultural participation, and other community and economic development issues.  Within these broad areas, he specialized in community-based initiatives, local government policies, multi-party collaborations, performance measurement and community impact analysis.

Sarah Rankin

Senior Research Associate

Sarah Rankin is a Senior Research Associate at the Local Initiative Support Corporation. As part of LISC's Research & Assessment unit, she manages the evaluation of the Sustainable Communities Initiative, a ten-city expansion of a comprehensive community development model developed by LISC Chicago. At LISC she has previously worked as part of the Program Planning & Knowledge Sharing departments, tracking the organization's program activity and researching and sharing best practices. Prior to joining LISC, Ms. Rankin was a Program Manager at the Corporation for Enterprise Development, where she helped launch a children's savings program demonstration, SEED (Savings for Education, Entreprenuership, and Downpayment) and did state policy work on asset-building programs for working families. Other experience includes work on the initial setup of the New Markets Tax Credit Program at the Self-Help Ventures Fund in Durham, North Carolina and coordination of classroom grants and teacher fellowships for the San Francisco Education Fund. Ms. Rankin received a BA in History from Yale University and a Master's in Public Policy from Duke University.

Francisca Winston

Research Associate

A Research Associate at LISC since September 2005, Francisca has an academic background in mathematics, statistics and public policy. After constructing the Neighborhood Monitoring Database, she is now exploring its uses for the Sustainable Communities Quantitative Assessment and other work. In addition, Francisca applies her GIS mapping skills to a variety of projects at LISC. She contributes to R&A’s ongoing analysis of high cost and subprime home mortgage loans and created maps of all LISC local program areas to identify neighborhoods at highest risk of concentrated foreclosure.

Francisca has an undergraduate degree in mathematics from Williams College and earned a master’s in Public Policy and Management at Carnegie Mellon University in 2005.

Data Partners

Indianapolis: The Polis Center at Indiana University Purdue University Indianapolis (Polis)

Sharon Kandris, Michelle Derr

The Polis Center is an academic research center within the IU School of Liberal Arts. Polis focuses on community-based research and analysis and advanced information technologies, especially geographic information systems (GIS). The Center's purpose is to build understanding of community issues from a variety of perspectives. The Center’s Social Assets and Vulnerabilities Indicators (SAVI) system is an electronic database that includes data on community assets such as schools, churches and community centers, as well as information on community vulnerabilities such as crime, safety, poverty and health. SAVI is a joint project of the United Way/Community Service Council of Central Indiana and the Polis Center. The United Way/CSC handles SAVI training and community outreach, while Polis provides research assistance and collects, analyzes and maps the data, which covers the Indianapolis metropolitan area. SAVI is intended to help human service agencies, governments, community organizations, and individuals conduct research, as well as engage in planning, community development and policy making.

Milwaukee: The Nonprofit Center of Milwaukee Neighborhood Data Center (NPCM)

Michael Barndt, Todd Claussen

NPCM is an association of nonprofit organizations in the Southeastern Wisconsin region committed to the empowerment of nonprofit organizations through community-based decision-making, leadership development, effective management, resource sharing, and other collaborative efforts.  As part of this mission, the Neighborhood Data Center is a technical resource that produces data, maps, reports, and analyses to allow organizations to better plan and develop programs that address the problems of Milwaukee neighborhoods. The Data Center acts as a data clearinghouse, collecting and organizing information valuable to understanding Milwaukee neighborhoods.  It addresses the needs of organizations serving Milwaukee neighborhoods with customized analysis, data, and GIS, and works to expand citizen access to information by the use of technology. The Data Center has worked on an array of local and national projects in areas such as crime, housing, and public health.

Rhode Island: The Providence Plan (ProvPlan)

Pat McGuigan, Jim Lucht

The Providence Plan was chartered to build partnerships among government agencies, civic groups, and concerned residents in pursuit of six primary goals: (1) to put people to work; (2) to retain the city's middle class; (3) to make neighborhoods safe and livable; (4) to improve the quality of the public schools; (5) to provide decent and affordable housing; and (6) to increase jobs and tax yields in downtown Providence. ProvPlan seeks to achieve these goals and others by building partnerships among City, State, and Federal agencies; business, labor, civic, and religious groups; community-based organizations; academic institutions; and concerned residents. ProvPlan has built and maintained a data warehouse with information about people, education, health, public safety, property, and housing, including a database that allows users to examine any of these issues by neighborhood, street, or individual address. ProvPlan acts as a community convener and as an incubator of new initiatives, particularly those with a direct link to its data and information work.

Twin Cities: Center for Urban and Regional Affairs, University of Minnesota (CURA)

Kris Nelson, Jeff Matson

CURA is an all-University applied research and technology center at the University of Minnesota that connects faculty and students with community organizations and public institutions working on significant public policy issues in Minnesota. CURA produces research on critical issues in the state of Minnesota, provides students opportunities for practical research experience, helps government agencies and community organizations get the research and personnel assistance they request, and enables the University of Minnesota to better fulfill its land grant and urban missions. CURA works across disciplinary lines and professional boundaries, creating new programs and supporting projects that meet needs that no one else is meeting. Its staff collaborates closely with other University units and with community constituents: nonprofit organizations, ethnic and racial minority groups, businesses, rural towns, inner-city neighborhoods, suburban communities, local governments, and state agencies.

Chicago: Metro Chicago Information Center (MCIC) – affiliated partner

Garth Taylor

MCIC is a neutral third party expert committed to generating strategic information that improves local and regional economic and quality of life conditions in communities. MCIC has a membership base of about 200 organizations, about 100 of which are organizations involved in community planning that use MCIC data and technical support for needs assessments, strategic plans, funding proposals, public education/advocacy reports, evaluations, and mandated inventories of service needs and/or assets in their catchment areas. MCIC is the data intermediary for the New Communities Program. It is substantially expanding its holdings of neighborhood level data to do this work, and is tasked with preparing maps, tabulations, and reports to determine the patterns of neighborhood change associated with the NCP work.

Attachment 3

First Year Sustainable Communities Workplan

National Research staff:

Prior to development of the quantitative analysis plan, LISC senior management reviewed and approved the overall research design, triggering hiring of the Project Manager and execution of contracts with national research consultants and local data partners.   Management also approved selection of impact sites.  Staff developed the qualitative analysis plan and accompanying data collection instruments and protocols.  First-year tasks for the quantitative analysis included:

- Team review of the Quantitative Analysis Plan covering construction of the National Neighborhood Monitoring Database and testing of monitoring variables, and assembly of analysis data from impact sites.

- Integration of local quantitative analysis plans in the overall plan, and development of reporting formats for the neighborhood monitoring and the national assessment reports.

- Analysis of national and local data, together with results from the qualitative analysis, to draft an annual report to LISC board synthesizing results from all sites.

- Identification of additional topical analyses, drawing on local and national quantitative data as appropriate, which will further pursue specific findings from the cross-site analysis.

National Neighborhood Monitoring Database

The national neighborhood monitoring database was constructed.  Staff completed initial analysis of census and other data to construct profiles of all target neighborhoods.  Local LISC submitted information on the boundaries of target neighborhoods, and in most cases, have identified neighborhoods suitable for use as analysis neighborhoods.  Other tasks included:

- Development of analysis metrics and techniques included in annual neighborhood monitoring reports, including development of comparison neighborhood methodology in concert with local data partner comparison neighborhood selection.

- Data updates as data sources make additional time periods available, acquisition, cleaning, and integration of updated data into NNMD.

- Annual Neighborhood Monitoring Reports created for each target neighborhood in all 16 Sustainable Communities sites included in this assessment. Neighborhood monitoring reports in impact Sites have been generated in conjunction with the Data Transfer task under Local Data Partners.

Local Data Partners

Analysis staff have selected impact sites and contracted with data partners in those sites.  First-year tasks included:

- Delivery of data reconnaissance reports by data partners, detailing available data in the areas of housing & real estate, economy & work force, income & wealth, community quality and safety, community institutions & relationships, demographics & health indicators, and education & culture. Data availability is documented by data source, level of geography available, dates covered, data quality, release restrictions, and expense. Data reconnaissance reports are used to inform the selection of indicators in the local quantitative analysis plans.

- Selection of comparison neighborhoods, based on methodology developed collaboratively by LISC R&A, national consultants, and local data partners.  Comparison neighborhoods are used to gauge the relative performance of SC target neighborhoods.

- Initial summary tables from data partners, summarizing indicators by target and comparison neighborhood for data which is available in-house and easily aggregated.

- Creation of local quantitative analysis plans by data partners, specifying data sources and metrics to be used in the analysis. Analysis plans will reflect the availability of data from both local and national sources and the neighborhood change goals expressed in neighborhood plans developed through the local LISC Sustainable Communities effort.

- Transfer of data tables. Local data partners transferred to LISC R&A data tables of all data used in local analysis plans.  LISC R&A transferred to local partners data from the National Neighborhood Monitoring Database required to fill local data gaps and maintain consistency of data treatment across local data partners.

- Baseline Neighborhood Monitoring Reporting containing information on target neighborhood conditions and previous trends relative to comparison neighborhoods, other low-income neighborhoods, and the remainder of the city.  The reports also contain maps and graphics displaying results for a subset of variables, which include those of primary interest to neighborhood stakeholders.

- Annual Neighborhood Monitoring Reporting, presenting updated data in relation to baseline values. Basic statistical tests will be performed on selected measures to determine whether changes in target neighborhoods are significantly different from other geographies within the city. As with the Baseline Report, the Annual Neighborhood Monitoring Report will consist primarily of data tables and summary statements of findings, with maps of selected variables.

# Footnotes

Local Initiatives Support Corporation, Sustainable Communities Assessment Qualitative Analysis Plan, March 12, 2008.

See Miller, Anita and Tom Burns (2006). “Going Comprehensive: Anatomy of an Initiative that Worked – CCRP in the South Bronx. ” (Philadelphia: OMG Center for Collaborative Learning, December, 2006.).

A note on nomenclature: throughout this paper, the term “community” will be used to refer to neighborhoods; the term “site” or “jurisdiction” or “program area” will be used to refer to the cities selected as Sustainable Communities demonstration sites.

Tom Dewar and Michael Bennett, “Review of the New Communities Program: Towards Effective Implementation of Neighborhood Plans,” MacArthur Foundation grant review, October, 2006.

These sites are

These include Bay Area, Detroit, Duluth, Kansas City, Indianapolis, Milwaukee, Rhode Island, and Twin Cities.

Including the original program site in Chicago, there are 17 sites in the Sustainable Communities initiative.  Because the Chicago effort is being evaluated separately, this analysis will cover the 16 remaining sites.

More information can be found at www.urban.org/NNIP.

“Comprehensive Indicators of Neighborhood Character and Change:  Monitoring LISC’s Sustainable Communities Initiative.”  Local Initiatives Support Corporation, August 21, 2007.

In the last year or so, address vacancy data from the US Postal Service, as assembled and distributed by the US Department of Housing and Urban Development, has become available.  These data are used in neighborhood monitoring, but did not cover the time period of interest for defining comparison neighborhoods.

This was a good discriminator in the MDRC cluster analysis used to classify Chicago neighborhoods.

This approach follows the lead of the MDRC analysis of the Chicago New Communities Program.

Transparency alone is one of the strongest reasons to use this method instead of propensity scoring, which would appear to be the next best alternative.   See Oakes and Johnson (2006) and as applied to spatial interventions, Rich and Stoker (2009, forthcoming)

Galster, George, Diane Levy, Noah Sawyer, Kenneth Tempkin and Christopher Walker. 2005. The Impact of Community Development Corporations on Urban Neighborhoods. Washington, DC: The Urban Institute.

Principal variables, spatial resolution, data sources and other information on the contents of the database are contained in LISC “Description of the National Neighborhood Monitoring Database, February, 2008.

Teune and Przeworszky, The Logic of Comparative Inquiry.

LISC Research and Assessment, “Statistical Comparisons of Sustainable Communities Neighborhoods,” February 19, 2008.

This dual accountability may well turn out to be problematic in some sites, but this seems unavoidable given the strong local interest in making use of assessment results in implementation.